|  | CQC Cloud Platform Build Roadmap Plan Five-phase delivery plan for completing the cloud platform build |
| --- | --- |

|  | Purpose This plan converts the current cloud platform task list into a sequenced roadmap with clear phases, delivery workstreams, dependencies, milestones, governance checkpoints and delivery controls. |
| --- | --- |

| Property | Value |
| --- | --- |
| Document owner | Platform Engineering |
| Author | Alastair Turton, Platform Engineering Manager |
| Classification | Internal Use Only |
| Status | Draft for Review |
| Version | 0.1 |
| Created date | 07 July 2026 |
| Review cadence | Monthly during active delivery; quarterly once in BAU |

# 1. Executive Summary

The Cloud Platform Build Roadmap Plan defines a pragmatic five-phase approach to complete the platform foundation, standardise operating controls, deliver security and connectivity capabilities, productionise DevOps, and then transition the legacy estate onto the target platform. The plan is intended to support governance review, delivery sequencing and Azure DevOps backlog alignment.

The roadmap groups the current task list into delivery phases so that dependent capabilities are completed in the right order. This avoids parallel activity creating avoidable contention across networking, DNS, firewall, identity, policy, FinOps and migration workstreams.

|  | Roadmap principle Build the minimum complete platform foundation first, then standardise controls, productionise operational processes, and only then accelerate legacy migration and optimisation. |
| --- | --- |

# 2. Scope

This plan covers the cloud platform build activities provided in the current task list. It focuses on platform-level services and controls that enable workload delivery, onboarding, migration and operational support.

| In scope | Out of scope / managed separately |
| --- | --- |
| Azure networking, DNS, Private DNS, AMPLS, DNS Resolver, VNET peering and AVNM | Application-specific functional delivery and product feature roadmaps |
| Firewall base rules, Firewall Manager use and Littlefish handover | Detailed firewall rule implementation scripts or change records |
| CQC Azure Policy update and CCoE approval route | Enterprise governance committee terms of reference beyond this plan |
| FinOps Hub, reporting workflow and cost management process | Detailed chargeback/showback model design unless agreed as a separate work package |
| Legacy discovery, migration and transformation sequencing | Full workload-by-workload migration runbooks |
| DevOps productionisation for platform delivery | Detailed sprint backlog unless exported into Azure DevOps separately |

# 3. Delivery Model

The roadmap is structured as five delivery phases. Each phase has a clear objective, key deliverables, completion criteria and governance checkpoint. Delivery can overlap where dependencies permit, but stage gates should be used to prevent downstream work from proceeding before the required platform controls are stable.

| Phase | Name | Objective | Primary milestone |
| --- | --- | --- | --- |
| 1 | Foundation & Governance | Approve operating model, establish CCoE route, update policy baseline and initiate platform-level control framework. | Governance baseline approved |
| 2 | Core Platform Services | Complete networking, DNS and identity foundations required by workloads and shared services. | Strategic networking services operational |
| 3 | Security & Operations | Implement AMPLS, firewall base rules, handover model and operational security controls. | Secure platform operating model complete |
| 4 | Engineering Excellence | Productionise DevOps, standards, repositories, pipelines, release controls and IaC ways of working. | Enterprise DevOps platform operational |
| 5 | Legacy Transformation | Discover, plan, migrate and transform legacy workloads onto the target platform. | Legacy migration programme mobilised |

# 4. Phase Plan

## Phase 1 - Foundation & Governance

Establish the governance, approval and control framework required to complete the platform build in a controlled manner.

| Area | Detail |
| --- | --- |
| Key deliverables | • CCoE implementation and approval • CQC Azure Policy update • Initial governance route and decision checkpoints • FinOps reporting workflow design aligned to future FinOps Hub capability |
| Dependencies | • Executive or governance sponsor agreement • Platform ownership model confirmed • Policy baseline agreed by Platform and Security |
| Completion criteria | • CCoE approval route documented • Azure Policy update backlog agreed • Roadmap decision log created • Governance checkpoint ready for phase exit |
| Primary owner | Platform Engineering with Security, Architecture and governance stakeholders |
| Initial RAG view | Amber until CCoE approval is confirmed |

## Phase 2 - Core Platform Services

Complete the common networking, DNS and identity platform capabilities required by landing zones, platform services and workload onboarding.

| Area | Detail |
| --- | --- |
| Key deliverables | • VNET peering rationalisation • DNS Resolver implementation • Private DNS migration including unused resource/resource group identification • Public cqc.org.uk DNS migration into Azure • VPN DNS and VNET range changes • AVNM implementation • New IMS Domain Controllers delivered by Littlefish |
| Dependencies | • Agreed network target state • Addressing and DNS impact assessment • Littlefish delivery engagement for IMS Domain Controllers • Change windows and rollback plans |
| Completion criteria | • DNS resolver service operational • Private and public DNS migration paths approved • VNET peering model documented • AVNM adoption route confirmed • Identity dependency for IMS Domain Controllers understood |
| Primary owner | Platform Engineering with Littlefish where delivery is assigned |
| Initial RAG view | Amber because DNS, VPN and identity changes are dependency-heavy |

## Phase 3 - Security & Operations

Implement secure connectivity, monitoring access paths and firewall operating controls so the platform is supportable and governable.

| Area | Detail |
| --- | --- |
| Key deliverables | • AMPLS implementation • New firewall base rule implementation using Firewall Manager • Firewall handover to Littlefish • Operational evidence packs and support handover notes • Policy validation after implementation |
| Dependencies | • Core networking and DNS resolver services • Firewall Manager design and rule model agreed • Littlefish support model and RACI confirmed • Monitoring destinations and private link scope design confirmed |
| Completion criteria | • Firewall base rule set implemented and validated • AMPLS connectivity validated • Firewall handover pack accepted • Operational ownership and escalation path documented |
| Primary owner | Platform Engineering, Security and Littlefish |
| Initial RAG view | Amber until firewall handover and AMPLS validation are complete |

## Phase 4 - Engineering Excellence

Productionise DevOps so platform change is delivered consistently through repositories, pipelines, approvals, standards and repeatable automation.

| Area | Detail |
| --- | --- |
| Key deliverables | • DevOps productionisation • Repository and branching standards • Pipeline standards and stage gates • Terraform module usage and IaC delivery controls • Release and evidence workflow for platform changes |
| Dependencies | • CQC Azure Policy baseline • CCoE approval route • Platform standards and naming/tagging alignment • ServiceNow or work item workflow alignment where applicable |
| Completion criteria | • Production release path defined • Main branch control and review model documented • Pipeline stage gates agreed • IaC evidence available for material changes |
| Primary owner | Platform Engineering |
| Initial RAG view | Green once standards and release controls are adopted |

## Phase 5 - Legacy Transformation

Move from platform build into controlled discovery, transformation and migration of legacy services onto the target cloud platform.

| Area | Detail |
| --- | --- |
| Key deliverables | • Legacy discovery • Legacy transformation and migration plan • Migration dependency map • Workload readiness assessment • Decommissioning route for displaced legacy services |
| Dependencies | • Core platform services ready • Security and support model complete • DevOps productionisation mature enough to support repeatable changes • Workload owners available for discovery and migration planning |
| Completion criteria | • Legacy discovery register completed • Prioritised migration backlog produced • Migration wave plan approved • Risks and acceptance criteria agreed for first migration wave |
| Primary owner | Platform Engineering with Architecture, Security and workload teams |
| Initial RAG view | Amber until discovery confirms migration complexity |

# 5. Roadmap Timeline View

The timeline below is a planning view. Dates should be refined once resource availability, change windows and governance approvals are confirmed.

| Quarter | Phase focus | Key activities | Expected outcome |
| --- | --- | --- | --- |
| Q3 2026 | Phase 1 and Phase 2 start | CCoE approval, Azure Policy update, VNET peering, DNS Resolver, IMS Domain Controller planning, initial FinOps Hub mobilisation | Governance and shared service foundations initiated |
| Q4 2026 | Phase 2 and Phase 3 | Private DNS migration, public cqc.org.uk DNS migration, VPN DNS and VNET range changes, AVNM, AMPLS, firewall base rules | Core platform networking and security controls operational |
| Q1 2027 | Phase 3 and Phase 4 | Firewall handover to Littlefish, FinOps Hub, FinOps workflow, DevOps productionisation | Operational control and engineering delivery model stabilised |
| Q2 2027 | Phase 5 mobilisation | Legacy discovery, migration dependency mapping, legacy transformation plan, first migration wave preparation | Migration programme ready to proceed under governed controls |
| Q3 2027 | Optimisation and BAU transition | Refine controls, measure adoption, address residual debt, move roadmap into continuous improvement | Platform build transitions into steady-state optimisation |

# 6. Detailed Work Package Register

| ID | Workstream | Deliverable | Phase | Owner | Priority | Status |
| --- | --- | --- | --- | --- | --- | --- |
| GOV-01 | Governance & Operating Model | CCoE implementation and approval | Phase 1 | Platform Engineering | High | Not Started |
| GOV-02 | Governance & Operating Model | CQC Azure Policy update | Phase 1 | Platform / Security | High | Not Started |
| NET-01 | Networking & Connectivity | VNET peering rationalisation | Phase 2 | Platform Engineering | High | Planned |
| DNS-01 | Networking & Connectivity | DNS Resolver implementation | Phase 2 | Platform Engineering | High | Planned |
| DNS-02 | Networking & Connectivity | Private DNS migration and unused resource/RG identification | Phase 2 | Platform Engineering | High | Planned |
| DNS-03 | Networking & Connectivity | Public cqc.org.uk DNS migration into Azure | Phase 2 | Platform Engineering | High | Planned |
| NET-02 | Networking & Connectivity | VPN DNS and VNET range changes | Phase 2 | Platform Engineering / LF | High | Planned |
| NET-03 | Networking & Connectivity | AVNM implementation | Phase 2 | Platform Engineering | Medium | Planned |
| ID-01 | Identity Services | New IMS Domain Controllers | Phase 2 | Littlefish | High | Planned |
| SEC-01 | Security & Operations | AMPLS implementation | Phase 3 | Platform Engineering | High | Planned |
| SEC-02 | Security & Operations | New firewall base rule implementation via Firewall Manager | Phase 3 | Platform / Security | High | Planned |
| SEC-03 | Security & Operations | Firewall handover to Littlefish | Phase 3 | Platform / Littlefish | High | Planned |
| FIN-01 | FinOps | FinOps Hub | Phase 3/4 | Platform Engineering / FinOps | High | Planned |
| FIN-02 | FinOps | FinOps reporting and workflow | Phase 3/4 | Platform Engineering / FinOps | High | Planned |
| DEV-01 | Engineering Excellence | DevOps productionisation | Phase 4 | Platform Engineering | High | Planned |
| MIG-01 | Legacy Transformation | Legacy discovery | Phase 5 | Platform / Architecture / Workloads | High | Planned |
| MIG-02 | Legacy Transformation | Legacy transformation and migration | Phase 5 | Platform / Workloads | High | Planned |

# 7. Dependencies and Control Points

| Dependency | Impacted deliverables | Control point |
| --- | --- | --- |
| CCoE approval and governance route | Azure Policy update, DevOps productionisation, legacy migration approvals | Phase 1 exit checkpoint |
| Network target state and address plan | VNET peering, VPN DNS and VNET range changes, AVNM | Network design review |
| DNS Resolver readiness | Private DNS migration, public cqc.org.uk DNS migration, AMPLS access patterns | DNS migration readiness review |
| Littlefish delivery and support engagement | IMS Domain Controllers, firewall handover, operational support transition | Supplier handover acceptance |
| Firewall Manager rule model | New firewall base rule implementation and future workload onboarding | Security design approval |
| DevOps production readiness | Repeatable platform changes, migration wave delivery, evidence capture | Release governance checkpoint |
| Legacy discovery quality | Migration wave planning and transformation sequencing | Migration readiness assessment |

# 8. RACI Summary

This RACI is a starting point for review. It should be validated with Security, Architecture, FinOps, workload owners and Littlefish before formal approval.

| Activity | Platform Engineering | Security | Architecture | Littlefish | FinOps | Workload Teams |
| --- | --- | --- | --- | --- | --- | --- |
| CCoE implementation and approval | A/R | C | C | I | C | I |
| Azure Policy update | A/R | C/R | C | I | C | I |
| DNS Resolver and DNS migrations | A/R | C | C | C/R | I | C |
| New IMS Domain Controllers | A | C | C | R | I | I |
| AMPLS implementation | A/R | C | C | C | I | I |
| Firewall base rules and handover | A/R | C/R | C | R | I | I |
| FinOps Hub and reporting workflow | C/R | I | I | I | A/R | C |
| DevOps productionisation | A/R | C | C | I | I | C |
| Legacy discovery and migration | A/R | C | C/R | C | C | R |

# 9. Risks, Issues and Assumptions

| ID | Type | Description | Mitigation / action |
| --- | --- | --- | --- |
| R1 | Risk | DNS, VPN and VNET changes could have wide operational impact if sequencing and rollback are not handled carefully. | Complete impact assessment, agree change windows, validate rollback plans and document acceptance criteria before migration. |
| R2 | Risk | CCoE approval delays could slow policy updates and DevOps productionisation. | Run governance approvals as an early Phase 1 dependency and maintain a decision log. |
| R3 | Risk | Firewall handover may be incomplete if ownership, support model and runbooks are not accepted by Littlefish. | Define handover acceptance criteria before implementation, including rule ownership, escalation, monitoring and change process. |
| R4 | Risk | Legacy migration complexity may be underestimated before discovery completes. | Treat discovery as a formal phase with evidence capture, dependency mapping and wave planning. |
| A1 | Assumption | Platform Engineering remains accountable for platform standards, tooling and control design. | Validate through CCoE and programme governance. |
| A2 | Assumption | Littlefish will implement or support specific deliverables where noted, including IMS Domain Controllers and firewall handover. | Confirm supplier delivery scope, acceptance criteria and accountable contacts. |

# 10. Governance and Reporting Cadence

The roadmap should be governed through a lightweight but disciplined delivery cadence. The aim is to maintain visibility across dependencies, risks and decisions without creating avoidable overhead.

| Cadence | Forum / artefact | Purpose | Output |
| --- | --- | --- | --- |
| Weekly | Platform delivery review | Track progress, unblock issues, confirm next actions | Updated work package register and action log |
| Fortnightly | Technical checkpoint | Review architecture, DNS, networking, firewall and DevOps dependencies | Technical decisions and dependency updates |
| Monthly | Governance checkpoint | Report milestone progress, RAG status, risks and decisions needed | Executive roadmap update and decision log |
| Phase exit | Stage gate review | Confirm completion criteria and readiness to proceed | Approved phase closure or remediation actions |

# 11. Recommended Next Steps

Validate the five-phase structure with Platform Engineering, Security, Architecture and Littlefish.

Confirm owner and accountable approver for each work package.

Add target dates, effort estimates and sprint allocation to the work package register.

Convert work packages into Azure DevOps Epics, Features and Tasks.

Agree the first Phase 1 governance checkpoint and phase-exit criteria.

# Appendix A - Azure DevOps Mapping

| Roadmap phase | Suggested Azure DevOps Epic | Example Features |
| --- | --- | --- |
| Phase 1 | Cloud Governance & CCoE | CCoE approval; Azure Policy update; roadmap governance |
| Phase 2 | Azure Networking Modernisation | VNET peering; DNS Resolver; Private DNS; Public DNS; VPN changes; AVNM |
| Phase 2 | Identity Services Modernisation | New IMS Domain Controllers |
| Phase 3 | Platform Security & Operations | AMPLS; firewall base rules; firewall handover |
| Phase 3/4 | FinOps Capability | FinOps Hub; FinOps reporting workflow |
| Phase 4 | Enterprise DevOps Platform | DevOps productionisation; repos; pipelines; IaC standards |
| Phase 5 | Legacy Estate Migration | Legacy discovery; transformation and migration waves |

# Appendix B - Source Task List

The following original task list was provided and grouped into the plan above:

VNET Peering

Private DNS Migration - identification of unused resources or resource groups to examine

Public cqc.org.uk DNS migration into Azure

AMPLS

DNS Resolver implementation

New IMS Domain Controllers - Littlefish

VPN DNS and VNET range changes

AVNM Implementation

New Firewall Base rule implementation - Firewall Manager

Firewall handover to Littlefish

CQC Azure Policy update

FinOps Hub

FinOps reporting and workflow

CCoE implementation and approval

Legacy Discovery

Legacy transformation and Migration

DevOps Productionisation

|  | Document note This document has been created without copying the official CQC logo artwork. It uses a CQC-style internal document treatment and should be aligned to the official Word letterhead or brand template before external distribution. |
| --- | --- |