CLOUD ASSESSMENT

Executive Summary

PREPARED FOR Care Quality Commission

| Document Reference: | CQC-CLOUD-ASSESS-EXEC-001 |
| --- | --- |
| Version: | 0.1 — DRAFT |
| Classification: | OFFICIAL — Internal / Confidential |
| Date: | 17 July 2026 |
| Prepared by: | [Name, Title] |
| Organisation: | Care Quality Commission (CQC) |
| Source Assessment: | Hitachi Solutions Europe — ACS_920 / 921 / 922 |
| Cloud Region (Primary): | UK South |
| Cloud Region (Secondary): | UK West |

# 1. Executive Summary

This document is a consolidated summary of the CQC Cloud Assessment delivered by Hitachi Solutions Europe. It draws together the four assessment outputs — the Cloud Assessment Playback (ACS_920), the Cloud Assessment Report (ACS_921), the Cloud Health Check (ACS_922) and the Cloud Strategy Workshop — into a single detailed narrative, and sets out the prioritised work packages that turn the findings into a sequenced, governed programme of delivery.

The assessment established three things:

- CQC's cloud strategy is sound. The target direction is clear and consistent across the CCoE charter, the cloud strategy paper and every workshop: a CAF-aligned landing zone, stronger governance, better observability, cost transparency, Zero Trust, and a platform that supports data-driven regulation.

- The current estate cannot yet deliver on that direction. Governance is split across three management-group hierarchies, policy enforcement varies by subscription placement, standing privilege is high, observability is fragmented and cost attribution is not possible. Every technical chapter describes a different facet of the same problem: the organisation is trying to move forward while carrying an estate that is not yet controlled.

- Work is already underway — it lacks coordination. CQC is not starting from zero: the platform team is building the new landing zone, security is improving identity hygiene, and FinOps analysis is identifying waste. The issue is not a lack of activity but a lack of a single view of what should come first, what depends on what, and who arbitrates when priorities compete.

The assessment resolves into a 12-pillar maturity baseline, 129 prioritised recommendations, and sixteen owned, sequenced work packages delivered across three phases over roughly eighteen months. The aim is not to replace the work already underway, but to make it deliberate, sequenced and governed.

At a glance: £2.185M annualised Azure spend with zero cost-allocation tag coverage; 107 of 118 Key Vaults allow public network access; 0 of 161 Function Apps enforce authentication; all 12 API Management instances are publicly exposed; mean Secure Score 59.8% against a 75% target; identity and secret management both at maturity level 1 (Initial).

# 2. Maturity at a Glance

The estate scores against the twelve HCAF pillars (1 Initial → 5 Optimised). Identity, secrets and application services are the weakest at level 1 (Initial). The final column maps each pillar to the work package that lifts it to target.

| HCAF Pillar | Current | Target | Lead WP |
| --- | --- | --- | --- |
| Cloud Governance | Developing (2) | Managed | WP03, WP04 |
| FinOps & Cost Management | Developing (2) | Defined | WP12 |
| Management & Monitoring | Initial (1) | Defined | WP10 |
| Identity & Access | Initial (1) | Defined | WP05 |
| Network Security | Developing (2) | Managed | WP07 |
| External Exposure | Developing (2) | Managed | WP08 |
| Secret & Key Management | Initial (1) | Managed | WP09 |
| Data Services | Developing (2) | Defined | WP14, WP15 |
| Compute | Defined (3) | Managed | WP11 |
| Application Services | Initial (1) | Defined | WP11 |
| Storage | Developing (2) | Managed | WP11 |
| Operations & Backup | Developing (2) | Managed | WP10 |

# 3. Immediate Security Priorities

Eight findings are the highest-priority exposures and are recommended for immediate remediation in Phase 1, ahead of the wider programme (consolidated as work package WP02).

| Area | Sub-Area | Recommendation | Owner |
| --- | --- | --- | --- |
| Networking & Security | NSG & Segmentation | Lock down exposed management ports (RDP/SSH) | Platform |
| External Exposure | Public IP | Remove direct VM public IP exposure | Network |
| Secret & Key Mgmt | Public Access | Disable public network access on prod/pre-prod key vaults; front with Private Endpoints | Platform |
| Identity Management | Identity Infrastructure | Remove or re-validate former partner access in Production (e.g. KPMG / AIS) | Security |
| Identity Management | Privileged Access | Extend PIM to all Global Administrators | Security |
| Workloads | Network Isolation | Privatise the data tier; disable public access on SQL | Data |
| Workloads | Storage | Remediate critically exposed storage accounts | Platform |
| Workloads | Storage | Enforce a Storage Account baseline policy initiative | Platform |

# 4. Prioritised Work Packages

The 129 recommendations group into sixteen owned, sequenced work packages. Every recommendation rolls up to exactly one package, and each package carries a single accountable owner and a delivery phase. WP03 (CAF consolidation) and WP16 (migration) sit on the critical path and gate most other packages.

| WP | Work Package | Owner | Phase | Recs | Outcome / Description |
| --- | --- | --- | --- | --- | --- |
| WP01 | Programme & Operating Model Establishment | Programme | 1 | 2 | Stand up the Technical Programme Leadership group and the Run/Service teams that sequence, arbitrate and own the rebuild. |
| WP02 | Urgent Security Remediation | Security / Platform | 1 | 8 | Close the eight high-priority exposure findings immediately — management ports, public IPs, key vaults, former partner access, PIM, data tier and storage. |
| WP03 | Landing Zone & CAF Consolidation | Platform | 1 | 5 | Consolidate onto the new CAF hierarchy, freeze legacy placement, and standardise onboarding and subscription vending. |
| WP04 | Governance Guardrails & Policy-as-Code | Platform | 1–2 | 10 | Move policy from documentary to enforced; publish the policy catalogue, NSG coverage and hosting standards. |
| WP05 | Identity & Privileged Access Hardening | Security | 2 | 9 | Eliminate standing privilege and click-ops, migrate flows to managed identities, and govern the guest lifecycle. |
| WP06 | Threat Detection — Defender, Sentinel & B2C | Security | 2 | 8 | Right-size Defender coverage, rationalise Sentinel analytics, and own the B2C migration ahead of the 2030 deprecation. |
| WP07 | Network Topology & Connectivity | Network | 1–3 | 10 | Hub-and-spoke in code, per-region firewalls, DR strategy, private DNS, and retirement of legacy connectivity. |
| WP08 | External Exposure Reduction | Network | 2 | 3 | DDoS Network Protection, public-IP rationalisation, and premium firewall inspection. |
| WP09 | Secret & Key Management | Platform | 1–2 | 3 | Vault-scoped RBAC, purge protection and diagnostics, and resolution of the shared cross-environment vault. |
| WP10 | Observability & ITSM Uplift | Operations | 2 | 10 | Consolidate monitoring, fix alert routing, move dashboards to code, and stand up the native ServiceNow connector. |
| WP11 | Workload Security & Hosting Modernisation | Integration | 2 | 12 | Authenticate SQL / APIM / Functions, restrict exposure, and rationalise compute and App Service hosting. |
| WP12 | FinOps Operating Model & Cost Optimisation | FinOps | 2 | 12 | Tagging and chargeback, reservations, right-sizing, and a monthly FinOps cadence with cost as a design input. |
| WP13 | AIS Modernisation | Integration | 2–3 | 6 | Environment parity, the Five Patterns design authority, resource-group split, and AIS under code control. |
| WP14 | Data Governance & Compliance | Data | 1–2 | 10 | Recover Purview, apply GDPR retention, embed classification, and standardise encryption across AI services. |
| WP15 | Data & AI Platform Modernisation | Data | 2–3 | 20 | Target-state architecture, pipeline rationalisation, MLOps, AI exposure strategy, and legacy platform exit. |
| WP16 | Legacy Workload Migration & Estate Transition | Platform / Workload | 3 | 1 | Migrate or recreate the legacy spokes and workloads onto the new CAF hub and retire the legacy hierarchies. |

# 5. Delivery Roadmap

The work is grouped into three phases by readiness, over roughly eighteen months. Delivery stays with the Platform, Security and workload teams; a new Technical Programme Leadership group sets the order and owns the cross-workstream dependencies.

- Phase 1 — Continue, Enable & Stabilise (≈ months 0–3): stand up programme leadership, close the eight urgent security exposures, consolidate the CAF landing zone, and begin the governance, identity, network, secrets, cost and data-governance foundations. WP01, WP02, WP03 (+ WP04, WP07, WP09, WP12, WP14 begin).

- Phase 2 — Consolidate & Standardise (≈ months 3–9): replace one-off fixes with estate-wide standards, deliver threat detection, observability and workload modernisation, give cost a named owner, and run the first migration pilots. WP05, WP06, WP08, WP10, WP11 (+ WP13, WP15 begin).

- Phase 3 — Transform, Migrate & Modernise (≈ months 9–18): migrate the bulk of the legacy estate onto the new CAF hub and retire the legacy hierarchies; complete AIS and data-platform modernisation. WP16 (+ WP07, WP13, WP15 complete).

# 6. Immediate Priorities & Next Steps

The strategic direction is agreed and the target state is clear; the constraint is execution under pressure. The immediate priority is to establish coordination and close the most acute exposures, then lay repeatable foundations before migration begins in earnest.

- Stand up the Technical Programme Leadership group and agree a single accountable owner and cadence (WP01).

- Close the eight high-priority security exposures (WP02).

- Consolidate onto the new CAF hierarchy and freeze legacy placement (WP03).

- Establish FinOps tagging and showback so cost informs sequencing (WP12); recover Purview to unblock data classification (WP14, D7).

- Resolve the ExpressRoute circuit-1 decommissioning (D13) ahead of the year-end data centre closure.

- Ratify the sixteen work packages, owners and phase sequence with the CCoE and CDIO, and adopt the dependency map as the programme's sequencing tool.

A fuller treatment of every domain finding, the target operating model and the full cross-workstream dependency map is provided in the companion document, “CQC Cloud Assessment — Detailed Summary & Prioritised Work Packages”.